## Repair Cafe planner
REPAIR CAFE PLANNER
| Task | Who's doing it? | Costs | Deadline | Done? | Notes
1 | Hold an organisers meeting to assign tasks
2 | Find possible venue and assess suitability with checklist
3 | Choose date (check the calendar for toolkit availability)
4 | Book venue
5 | Take out insurance as required
6 | Book a Cambridgeshire Repair Cafe Network toolkit if required
7 | Set up a google repair cafe email account (if you want to take bookings using google forms)
8 | Recruit repairers locally
9 | Email requirements for additional repairers to the Cambridgeshire Repair Cafe Network to be included in the monthly call for repairers. The newsletter goes out on the first Thursday of the month. Requests should be in 2 days before the newsletter date.
10 | Book an e-waste bin from the Greater Cambridge Shared Waste Partnership by emailing vicky.lacey@scambs.gov.uk
11 | Set up booking method (e.g. google forms)
12 | Write events listing including date, time, venue, types of repair, cake offering, booking details and send to repairnetwork@cambridgecarbonfootprint.org to be added to the website
13 | Recruit general volunteers for on the day to run reception, cafe, take donations and take photos
14 | Contact CCF to book posters and information displays on carbon footprinting, the Cambridge Climate Charter and/or the Cambridge Climate Map
15 | Design Repair Cafe poster (you may want to include a QR code to direct people to your events listing on the CCF website)
16 | Print posters
17 | Distribute posers
18 | Write press release including pictures (contact CCF if you need any)
19 | Conduct risk assessment (re-visit the venue if necessary)
20 | Publicise event via local media, newsletters and social media one month before event
21 | Publicise event via local media, newsletters and social media 3 weeks before event
22 | Publicise event via local media, newsletters and social media two weeks before event
23 | Publicise event via local media newsletters and social media one week before event
24 | Check bookings as they come in and follow up with request for more information/check with repairers as required
25 | Close bookings once quota met (usually reserve about 30% of repairer time for walk ins)
26 | Assign repairs to repairers and create a jobs list for the day
27 | Email out booking slots
28 | Print all forms for the day: Repair Cafe Agreement and feedback forms printed double-sided (1 per repair), repairers log (1 per repairer), jobs list (1 per receptionist), registration form (1 shared between receptionists). Print more than you need - you can use them next time.
29 | Follow up on access arrangements to venue (e.g. pick up keys)
30 | Contact preceding and following Repair Cafes to make arrangements for toolkit pick up/drop off either directly or via Mackays
31 | Pick up toolkit
32 | Pick up displays from Cambridge Carbon Footprint if required
33 | Check sufficient cutlery, crockery, tea and coffee making facilities given number of repairers, general volunteers and expected visitors
34 | Buy/source everything for the cafe: different types of milk, squash, teas, coffees, cakes, allergy labels for cakes, cash float, price list
35 | Briefing for all general volunteers - who's doing what on the day, where to direct people
36 | Decorate the room (bunting is included in the toolkit)
37 | Outdoor signage encouraging walk ins and arrows showing where to go
38 | Safety briefing for repairers: RCDs, fire precautions, first aid
39 | Direct booked in repairs to their allocated repairers on the jobs list
40 | Triage walk-in repairs and ask them to wait in the cafe until suitable repairer becomes available
41 | Look after repairers and volunteers on the day - offer regular tea, coffee and cake to all day
42 | Pack up room and clean
43 | Lock up and leave as arranged with venue
44 | Send out thank you email (BCC) to repairers and volunteers including summary of feedback forms
45 | Feedback to Cambridgeshire Repair Cafe Network using feedback checklist
46 | Return toolkit to Mackays/pass on to next Repair Cafe
47 | Make £20 electronic transfer to cover toolkit consumables
48 | Return displays to Cambridge Carbon Footprint
49 | Ensure all personal information is deleted or stored in GDPR compliant manner
50 | Repair Cafe review/debrief meeting with organisational team and start planning your next one!