## Repair Cafe planner
REPAIR CAFE PLANNER
Resources in bold can be found on our Repair Cafe Organisers' Hub
| Task | Who's doing it? | Costs | Deadline | Done? | Notes
1 | Hold an organisers meeting to assign tasks
2 | Find possible venue and assess suitability with Venue checklist
3 | Choose date (check the CCF events page for dates of other Repair Cafes)
4 | Book venue
5 | Book a Cambridgeshire Repair Cafe Network toolkit - use link on Organisers Hub
6 | Set up a Restarters account for your Repair Cafe organising group and add an event using the Restarters Guidance
7 | Take out insurance as required in line with our Insurance Guidance
8 | Conduct a Risk Assessment using our template
9 | Set up a google repair cafe email account (if you want to take bookings using google forms)
10 | Recruit repairers locally
11 | Request additional repairers, if needed, from the Cambridgeshire Repair Cafe Network Repairers Register, using link on Organisers Hub, to be included in the monthly call for repairers. The newsletter goes out on the first Thursday of the month. Requests should be in 2 days before the newsletter date. Please remember to include a request for someone who is competent at PAT testing if you don't have somebody local
12 | Respond to offers to repair from repairers in the network. Offers will be sent to you the week after the newsletter goes out. The spreadsheet will automatically update if offers are made later in the month. Please respond to all offers even if it's just a holding message to let repairers know when you will be able to let them know whether their help is needed.
13 | If you are in City or South Cambs and there is no e-waste bin nearby, book an e-waste bin from the Greater Cambridge Shared Waste Partnership by emailing vicky.lacey@scambs.gov.uk. NOTE AS OF JUNE 2026 - THIS SERVICE HAS BEEN TEMPORARILY SUSPENDED
14 | Make sure that you have a competent PAT tester to support your Repair Cafe, in line with our PAT testing policy
15 | Set up booking system (see Booking system instructions & Example booking form)
16 | Recruit general volunteers for on the day to run reception, cafe, take donations and take photos
17 | Design Repair Cafe poster - template provided (you may want to include a QR code to direct people to your events listing on the CCF website)
18 | Print posters
19 | Distribute posters
20 | Write Press Release including pictures
21 | Publicise event via local media, newsletters and social media one month before event
22 | Publicise event via local media, newsletters and social media 3 weeks before event
23 | Publicise event via local media, newsletters and social media two weeks before event
24 | Publicise event via local media newsletters and social media one week before event
25 | Check bookings as they come in and follow up with request for more information/check with repairers as required
26 | Close bookings once quota met (we usually reserve one slot per repairer for walk ins)
27 | Assign repairs to repairers and create a jobs list for the day
28 | Email out booking slots
29 | Print all forms for the day: Repair Cafe Agreement and feedback forms printed double-sided (1 per repair), repairers log (1 per repairer), jobs list (1 per receptionist), registration form (1 shared between receptionists). Print more than you need - you can use them next time.
30 | Follow up on access arrangements to venue (e.g. pick up keys)
31 | Contact toolkit host to make arrangements for toolkit pick up/drop off
32 | Pick up toolkit
33 | Check sufficient cutlery, crockery, tea and coffee making facilities given number of repairers, general volunteers and expected visitors
34 | Buy/source everything for the cafe: different types of milk, squash, teas, coffees, cakes, allergy labels for cakes, cash float, price list
35 | Briefing for all general volunteers - we usually do this on zoom for 15 mins in the evening the week before - who's doing what on the day, where to direct people
36 | Pre-Repair Cafe email to all repairers (bcc): final jobs list, risk assessment, PAT policy, wifi code, parking and food availability
37 | Decorate the room (bunting is included in the toolkit)
38 | Outdoor signage encouraging walk ins and arrows showing where to go
39 | Safety briefing for repairers: RCDs, fire precautions, first aid
40 | Direct booked in repairs to their allocated repairers on the jobs list
41 | Triage walk-in repairs and ask them to wait in the cafe until suitable repairer becomes available
42 | Look after repairers and volunteers on the day - offer regular tea, coffee and cake to all day
43 | Pack up room and clean
44 | Lock up and leave as arranged with venue
45 | Enter your item data into the Restart Fixometer using the Restarters Guidance in order to estimate the emissions savings and waste prevented by your Repair Cafe and support the Open Repair Alliance campaign for the right to repair
46 | Send out thank you email (BCC) to repairers and volunteers including summary of feedback forms
47 | Feedback to Cambridgeshire Repair Cafe Network using post-Repair Cafe Feedback Form
48 | Return toolkit
49 | Ensure all personal information is deleted or stored in GDPR compliant manner
50 | Repair Cafe review/debrief meeting with organisational team and start planning your next one!
Last updated: June 2026